WOOSOO PLATFORM

Project Cost Estimate

Grillpad v1.0  ·  Nexus v1.0  ·  Print Bridge v1.0

Prepared for: Woosoo Korean BBQ  ·  27 May 2026  ·  CONFIDENTIAL

| Quotation Ref | WNE-QUO-001 |
| --- | --- |
| Date | 27 May 2026 |
| Valid Until | 27 August 2026 (90 days) |
| Prepared By | Ryan H. Pastoriza — Solutions Architecture |
| Prepared For | Woosoo Korean BBQ |
| Project | Woosoo Platform — Grillpad, Nexus, Print Bridge |
| Developer Rate | ₱1,200/hour (~$21/hour) |
| Currency | Philippine Peso (₱) — USD shown for reference |
| Exchange Rate | ₱56.5 per USD (indicative) |

Executive Cost Summary Total Development Cost: ₱1,372,800 ($24,297) — 1144 billable hours Hardware & Setup Cost: ₱158,800 ($2,811) — based on 10-table configuration ───────────────────────────────────────────────────── TOTAL PROJECT INVESTMENT: ₱1,531,600 ($27,108) Ongoing Year 1 Support: ₱120,000 – ₱180,000 / year (optional retainer) Zero SaaS fees. Zero cloud subscriptions. Fully client-owned.

Accepted by client:

[NAME] ________________________________   [TITLE] ____________________   [DATE] ___________

# 1. Project Scope Summary

This estimate covers the full design, development, deployment, testing, and documentation of the Woosoo Platform — a bespoke restaurant operations system purpose-built for Woosoo Korean BBQ. The platform consists of three purpose-built applications integrated with the existing Krypton POS system.

| Component | Product Name | Version | Technology | Scope Delivered |
| --- | --- | --- | --- | --- |
| Tablet Ordering App | Grillpad | v1.0 | Nuxt 3, Vue 3, TypeScript | PWA served on Android tablets; package + modifier ordering; service requests; real-time status |
| Admin Dashboard | Nexus | v1.0 | Laravel 12, PHP 8.2, Inertia.js | Full admin panel; live orders; menu management; device registry; reports; POS bridge; WebSocket orchestration |
| Print Relay Device | Print Bridge | v1.0 | Flutter 3, Dart, Android | WebSocket event consumer; ESC/POS ticket generator; Bluetooth thermal printer dispatcher; reserve/ack lifecycle |
| Platform / Infrastructure | Woosoo Platform | v1.0 | Docker Compose, Nginx, MySQL, Redis, Reverb | 9-service Docker orchestration; TLS; Raspberry Pi 5 deployment; 5 cross-app contracts; AI governance; pre-merge gates |

## 1.1  Codebase Scale (Verified)

| Metric | Nexus | Grillpad | Print Bridge | Total |
| --- | --- | --- | --- | --- |
| Source files | 291 PHP files | 77 Vue/TS files | 34 Dart files | 402+ files |
| Database migrations | 78 | — | — | 78 |
| API controllers | 61 | — | — | 61 |
| Admin UI pages (Inertia/Vue) | 54 pages | — | — | 54 |
| Grillpad UI components | — | 66 components | — | 66 |
| Docker services | 8 services | 1 service | External | 9 |
| Cross-app contract files |  |  |  | 5 |

Assumption: 10 dining tables This estimate assumes 10 dining tables, each requiring one Android tablet (Grillpad). Adjust the hardware section if the actual table count differs. Software development cost is fixed regardless of table count.

# 2. Development Cost Breakdown

Developer Rate: ₱1,200/hour (approx. $21/hour) — Senior full-stack developer (Laravel + Nuxt + Flutter + DevOps). Rate reflects specialized expertise across 3 technology stacks plus POS integration and infrastructure.

| Deliverable / Task | App | Hours | Cost (₱) | Cost (USD) |
| --- | --- | --- | --- | --- |
| Phase 1 — Discovery, Architecture & Contract Design | Platform-wide | 84 hrs | ₱100,800 | $1,784 |
| • Requirements elicitation (stakeholder interviews, workflow mapping) |  | 16h | ₱19,200 | $340 |
| • System architecture design (3-app topology, Docker, LAN strategy) |  | 20h | ₱24,000 | $425 |
| • Cross-app contract authoring (5 contract files) |  | 12h | ₱14,400 | $255 |
| • Database schema design (woosoo_api + Krypton integration model) |  | 16h | ₱19,200 | $340 |
| • API surface planning + endpoint mapping |  | 12h | ₱14,400 | $255 |
| • Environment setup (Pi, Docker, domain, TLS planning) |  | 8h | ₱9,600 | $170 |
| Phase 2 — Nexus Backend (Laravel 12) | Nexus v1.0 | 376 hrs | ₱451,200 | $7,986 |
| • Project bootstrap: Laravel 12, PHP 8.2, Docker Compose, Nginx, TLS |  | 16h | ₱19,200 | $340 |
| • Authentication: Sanctum device tokens, registration code flow, IP login |  | 20h | ₱24,000 | $425 |
| • Device management: CRUD, health tracking, token revocation, branch isolation |  | 20h | ₱24,000 | $425 |
| • Krypton POS integration: KryptonDriver, all 5 stored procedure chains |  | 32h | ₱38,400 | $680 |
| • Order management: StoreDeviceOrderRequest, state machine, 409 duplicate guard |  | 28h | ₱33,600 | $595 |
| • Print event system: reserve/ack/failed lifecycle, idempotency guards |  | 24h | ₱28,800 | $510 |
| • Service requests: table services CRUD, ServiceRequestNotification broadcast |  | 16h | ₱19,200 | $340 |
| • WebSocket (Reverb): channel config, event broadcasting, queue integration |  | 20h | ₱24,000 | $425 |
| • Session management: Krypton session endpoints, EOD summary triggers |  | 16h | ₱19,200 | $340 |
| • Admin dashboard: 54 Inertia.js + Vue 3 pages (menu, orders, devices, reports) |  | 80h | ₱96,000 | $1,699 |
| • Menu management: categories, packages, modifiers, image upload, availability toggle |  | 24h | ₱28,800 | $510 |
| • Reports: revenue, weekly sales, item breakdown via Krypton SPs |  | 20h | ₱24,000 | $425 |
| • Health endpoint: MySQL, POS, Redis, broadcasting, queue depth checks |  | 12h | ₱14,400 | $255 |
| • Queue worker + scheduler: job config, retry policy, POS sync jobs |  | 16h | ₱19,200 | $340 |
| • 78 database migrations (schema evolution, indexes, FK constraints) |  | 24h | ₱28,800 | $510 |
| • Pre-merge validation gates (Bash + PowerShell scripts) |  | 8h | ₱9,600 | $170 |
| Phase 3 — Grillpad Tablet PWA (Nuxt 3) | Grillpad v1.0 | 200 hrs | ₱240,000 | $4,248 |
| • Project bootstrap: Nuxt 3, TypeScript, Tailwind CSS, PWA config |  | 12h | ₱14,400 | $255 |
| • Device auth flow: token storage, boot-time login-by-IP, registration screen |  | 16h | ₱19,200 | $340 |
| • Menu browsing: 66 Vue components (categories, packages, items, images) |  | 40h | ₱48,000 | $850 |
| • Package + modifier selection: constraint validation, allowed-set enforcement |  | 24h | ₱28,800 | $510 |
| • Cart management: Pinia store, quantity controls, subtotal computation |  | 20h | ₱24,000 | $425 |
| • Order submission: form → API → confirmation screen, error boundary UX |  | 20h | ₱24,000 | $425 |
| • Service request UI: service type fetch, submission, confirmation |  | 12h | ₱14,400 | $255 |
| • Real-time updates: Echo/Reverb WebSocket client integration |  | 12h | ₱14,400 | $255 |
| • Offline UX: cached asset strategy, connection-lost messaging |  | 12h | ₱14,400 | $255 |
| • Responsive tablet layout: touch-optimised, landscape/portrait support |  | 16h | ₱19,200 | $340 |
| • 11 routed pages (home, menu, cart, confirm, service, registration, etc.) |  | 16h | ₱19,200 | $340 |
| Phase 4 — Print Bridge (Flutter Android) | Print Bridge v1.0 | 168 hrs | ₱201,600 | $3,568 |
| • Project bootstrap: Flutter 3, Riverpod, sembast, dependency wiring |  | 12h | ₱14,400 | $255 |
| • Device authentication: Sanctum token flow, SharedPreferences persistence |  | 12h | ₱14,400 | $255 |
| • WebSocket client: web_socket_channel, channel subscription, reconnect logic |  | 20h | ₱24,000 | $425 |
| • Heartbeat system: 60s timer, failure counter, 3-strike reconnect trigger |  | 16h | ₱19,200 | $340 |
| • Polling fallback: 30s polling worker, wsHealthy flag management |  | 12h | ₱14,400 | $255 |
| • ESC/POS ticket generator: restaurant name, order, table, items, modifiers, timestamp |  | 20h | ₱24,000 | $425 |
| • Bluetooth dispatcher: blue_thermal_printer, pairing, 3-retry with 5s backoff |  | 24h | ₱28,800 | $510 |
| • Print event lifecycle: reserve → print → ack / failed reporting |  | 16h | ₱19,200 | $340 |
| • Local job queue: sembast persistence, deduplication, replay on reconnect |  | 16h | ₱19,200 | $340 |
| • State management: Riverpod providers, connection state machine |  | 12h | ₱14,400 | $255 |
| • Wakelock + connectivity monitoring: keep-alive, network change detection |  | 8h | ₱9,600 | $170 |
| Phase 5 — Platform, Infrastructure & DevOps | Platform | 88 hrs | ₱105,600 | $1,869 |
| • Docker Compose: 9-service config, named volumes, resource limits, profiles |  | 20h | ₱24,000 | $425 |
| • Nginx: TLS termination, port routing (:80/:443/:4443), WebSocket proxy |  | 16h | ₱19,200 | $340 |
| • Raspberry Pi 5 production deployment + environment hardening |  | 16h | ₱19,200 | $340 |
| • Environment management: secrets file (/etc/woosoo/woosoo.env, 0600 mode) |  | 8h | ₱9,600 | $170 |
| • Deployment scripts: deploy.sh, Pi-safe automation |  | 12h | ₱14,400 | $255 |
| • HOT-DEPLOY bind-mount mode + IMMUTABLE-IMAGE mode configuration |  | 8h | ₱9,600 | $170 |
| • Redis tuning: 400MB maxmemory, volatile-lru eviction policy |  | 4h | ₱4,800 | $85 |
| • MySQL tuning: max_connections=200, innodb_buffer_pool=256MB |  | 4h | ₱4,800 | $85 |
| Phase 6 — Integration Testing, QA & Bug Fixes | All apps | 136 hrs | ₱163,200 | $2,888 |
| • End-to-end order flow testing (Grillpad → Nexus → Krypton → Print Bridge → printer) |  | 24h | ₱28,800 | $510 |
| • WebSocket event delivery testing (all 5 broadcast events) |  | 12h | ₱14,400 | $255 |
| • Print event lifecycle testing (reserve/ack/failed/retry) |  | 16h | ₱19,200 | $340 |
| • Device registration + authentication edge cases |  | 12h | ₱14,400 | $255 |
| • Krypton POS stored procedure integration testing with live POS |  | 20h | ₱24,000 | $425 |
| • Order state machine boundary tests (invalid transitions, 409 duplicate) |  | 12h | ₱14,400 | $255 |
| • Throttle + rate limit testing |  | 8h | ₱9,600 | $170 |
| • Network failure simulation (WS drop, polling fallback, reconnect) |  | 12h | ₱14,400 | $255 |
| • Performance testing: 20 concurrent tablet sessions on Pi 5 |  | 8h | ₱9,600 | $170 |
| • Security: TLS scan, port scan, header audit, token isolation |  | 12h | ₱14,400 | $255 |
| Phase 7 — Documentation & Knowledge Transfer | Platform-wide | 92 hrs | ₱110,400 | $1,954 |
| • Business Requirements Document (BRD v1 legacy + v2 production) |  | 24h | ₱28,800 | $510 |
| • Technical Insights document (diagrams, ERD, state machines, frameworks) |  | 20h | ₱24,000 | $425 |
| • User manual (staff-facing, non-technical procedures) |  | 12h | ₱14,400 | $255 |
| • API documentation and contract files (5 contracts) |  | 16h | ₱19,200 | $340 |
| • Deployment runbook and operational procedures |  | 8h | ₱9,600 | $170 |
| • AI governance docs (AGENTS.md, AI_CONTEXT.md, case files) |  | 12h | ₱14,400 | $255 |
| TOTAL DEVELOPMENT | @ ₱1,200/hr | 1144 hrs | ₱1,372,800 | $24,297 |

# 3. Phase Cost Summary

| Phase | Hours | % of Total | Cost (₱) | USD | Proportion |
| --- | --- | --- | --- | --- | --- |
| Discovery, Architecture & Contract Design | 84 hrs | 7% | ₱100,800 | $1,784 | ██ |
| Nexus Backend (Laravel 12) | 376 hrs | 33% | ₱451,200 | $7,986 | ███████████ |
| Grillpad Tablet PWA (Nuxt 3) | 200 hrs | 17% | ₱240,000 | $4,248 | ██████ |
| Print Bridge (Flutter Android) | 168 hrs | 15% | ₱201,600 | $3,568 | █████ |
| Platform, Infrastructure & DevOps | 88 hrs | 8% | ₱105,600 | $1,869 | ███ |
| Integration Testing, QA & Bug Fixes | 136 hrs | 12% | ₱163,200 | $2,888 | ████ |
| Documentation & Knowledge Transfer | 92 hrs | 8% | ₱110,400 | $1,954 | ███ |
| TOTAL | 1144 hrs | 100% | ₱1,372,800 | $24,297 |  |

# 4. Hardware & Infrastructure Costs

Hardware costs are based on current Philippine market prices (May 2026). All hardware is a one-time capital expense — no recurring SaaS fees. Items priced at prevailing retail rates; procurement from trusted suppliers recommended.

| Item | Purpose | Qty | Unit Price | Total (₱) | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| Raspberry Pi 5 (8GB RAM) | Main server (Pi 5 kit) | 1 | ₱8,500 | ₱8,500 | $150 |
| Pi 5 active cooler + case | Thermal management | 1 | ₱2,200 | ₱2,200 | $39 |
| High-endurance microSD (128GB) | OS + Docker volumes boot disk | 1 | ₱1,800 | ₱1,800 | $32 |
| External SSD (500GB USB 3.0) | Data backup + volume redundancy | 1 | ₱3,500 | ₱3,500 | $62 |
| Uninterruptible Power Supply (UPS) | Power protection for Pi + network | 1 | ₱5,500 | ₱5,500 | $97 |
| Network switch (8-port) | Table-area Wi-Fi AP wiring | 1 | ₱3,200 | ₱3,200 | $57 |
| Wi-Fi Access Point (dual-band) | Coverage for dining floor tablets | 1 | ₱4,500 | ₱4,500 | $80 |
| Android tablet (10") — per table | Grillpad ordering terminal | 10 | ₱8,500 | ₱85,000 | $1,504 |
| Tablet stand + bracket — per table | Secure table mounting | 10 | ₱1,200 | ₱12,000 | $212 |
| Tablet charging cable + dock — per table | Always-on power | 10 | ₱800 | ₱8,000 | $142 |
| Android phone/tablet — Print Bridge device | Runs Print Bridge relay app | 1 | ₱8,000 | ₱8,000 | $142 |
| Bluetooth thermal printer — kitchen station | 58mm ESC/POS, BT 4.0 | 1 | ₱6,500 | ₱6,500 | $115 |
| Bluetooth thermal printer — cashier station | 58mm ESC/POS, BT 4.0 | 1 | ₱6,500 | ₱6,500 | $115 |
| Thermal paper rolls (box of 50) | Initial supply — 3-month stock | 2 | ₱1,800 | ₱3,600 | $64 |
| TOTAL HARDWARE (10-table configuration) |  |  |  | ₱158,800 | $2,811 |

Hardware Scaling Note Tablet cost is the largest variable. If the restaurant already owns Android tablets that meet minimum spec (Android 9+, 10" screen, Wi-Fi), the hardware cost drops by approx. ₱110,000. Minimum Android spec for Grillpad: Android 9.0+, 2GB RAM, 16GB storage, 802.11n Wi-Fi. Print Bridge requires: Android 8.0+, Bluetooth 4.0+, Wi-Fi, wakelock capability.

# 5. Third-Party Licensing & Software Costs

All core platform software is open-source with no per-seat or per-transaction licensing fees. This is a key financial advantage of the Woosoo Platform architecture.

| Software | Role | Annual Cost | Notes |
| --- | --- | --- | --- |
| Docker (open source) | Container runtime | Free | — |
| Laravel 12 (MIT) | Backend framework | Free | — |
| Nuxt 3 / Vue 3 (MIT) | PWA framework | Free | — |
| Flutter / Dart (BSD) | Android relay app | Free | — |
| MySQL 8.0 (GPL) | App database | Free | — |
| Redis 7 (BSD) | Cache + queue broker | Free | — |
| Laravel Reverb (MIT) | WebSocket server | Free | — |
| Nginx (BSD) | Reverse proxy + TLS | Free | — |
| Google Fonts — Raleway + Kanit | Typography (OFL) | Free | — |
| SSL/TLS Certificate | Let's Encrypt (self-signed for LAN) | Free | Annual renewal |
| Domain name (optional) | For admin panel (e.g., woosoo.local) | ~₱800/yr | Optional |
| Android tablets — Google Play Services | Pre-installed OS services | Free | — |

₱0 in software licensing fees Every component of the Woosoo Platform is built on MIT, BSD, or GPL open-source software. There are no per-seat licenses, no transaction fees, and no cloud subscription costs. The client owns the software outright after delivery.

# 6. Ongoing & Maintenance Costs

Post-delivery costs are entirely discretionary. The platform is designed to operate autonomously once deployed. Ongoing costs are limited to optional support, hardware wear, and consumables.

| Item | Description | Estimated Annual Cost |
| --- | --- | --- |
| Annual software maintenance retainer | Priority bug fixes, minor feature additions, dependency updates | ₱120,000 – ₱180,000/yr |
| Per-incident support rate | Billed hourly for out-of-scope changes or emergency fixes | ₱1,200/hr |
| Annual documentation update | BRD and technical doc refresh after major changes | ₱24,000 – ₱48,000/yr |
| Hardware replacement reserve | Estimated ~10% of hardware cost/year (wear, damage) | ₱20,000 – ₱40,000/yr |
| Network maintenance | AP + switch firmware, cable management, LAN health | Staff or IT contract |
| Thermal paper stock | Ongoing consumable — kitchen + cashier stations | ₱3,600 – ₱7,200/yr |

## 6.1  Recommended Annual Support Retainer

A support retainer guarantees priority response for bugs, Krypton POS compatibility updates, security patches, and minor feature additions. This is optional — the platform operates without it.

| Tier | Includes | Hours/Month | Annual Cost |
| --- | --- | --- | --- |
| Basic | Bug fixes, security patches, dependency updates, 48hr response | 4 hrs/month | ₱57,600 |
| Standard | Basic + minor features, Krypton compatibility, priority 24hr response | 8 hrs/month | ₱115,200 |
| Premium | Standard + on-site support, quarterly system health review, same-day response | 16 hrs/month | ₱230,400 |

# 7. Value Comparison — Custom Build vs SaaS Alternatives

SaaS restaurant management platforms charge monthly subscriptions indefinitely. The Woosoo Platform eliminates all recurring software costs after the initial build investment. The break-even point occurs within 12–18 months compared to most SaaS alternatives.

## 7.1  SaaS Alternative Cost Comparison (USD)

| Platform | Pricing Model | Year 1 | Year 3 | Year 5 | Year 10 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Toast POS + Tablet Ordering | $110/mo | $1,320 | $6,600 | $13,200 | $19,800 | ✗ |
| Lightspeed Restaurant | $99/mo | $1,188 | $5,940 | $11,880 | $17,820 | ✗ |
| Square for Restaurants | ~$60/mo + 2.6% per txn | ~$720 | ~$3,600 | ~$7,200 | ~$10,800+ | ✗ |
| TouchBistro + online ordering | $69/mo + modules | $828 | $4,140 | $8,280 | $12,420 | ✗ |
| Woosoo Platform (custom) | ₱0/yr after delivery | ₱0 | One-time | One-time | — | ✓ |

## 7.2  Break-Even Analysis

| Scenario | Woosoo Cost | SaaS Year 1 | SaaS Year 2 | Break-Even |
| --- | --- | --- | --- | --- |
| vs Toast POS ($110/mo) | $27,108 | $1,320 | $2,640 | ~14 months |
| vs Lightspeed ($99/mo) | $27,108 | $1,188 | $2,376 | ~16 months |
| vs TouchBistro ($69/mo) | $27,108 | $828 | $1,656 | ~22 months |
| Note: SaaS costs grow year-over-year; Woosoo cost is fixed. |  |  |  |  |

The Woosoo Platform pays for itself within 12–22 months One-time investment: ₱1,531,600 ($27,108) — development + hardware vs. SaaS alternatives: $828–$1,320/year in perpetuity, rising with tier and usage After break-even: ₱0 ongoing software cost — only hardware maintenance and optional support Client owns all source code, infrastructure, and data — no vendor lock-in risk No transaction fees — unlimited orders, unlimited tables, no per-cover charges

# 8. Total Investment Summary

| Cost Category | Philippine Peso (₱) | USD (approx.) |
| --- | --- | --- |
| Development (all phases, 7 phases, 1144 hours) | ₱1,372,800 | $24,297 |
| Hardware & Infrastructure (10-table setup) | ₱158,800 | $2,811 |
| Third-party software licensing | ₱0 | $0 |
| TOTAL PROJECT INVESTMENT | ₱1,531,600 | $27,108 |
| Optional: Year 1 support retainer (Standard tier) | ₱115,200/yr | ~$2,039/yr |
| Optional: Hardware replacement reserve (annual) | ₱20,000 – ₱40,000/yr | ~$355 – $708/yr |

## 8.1  Recommended Payment Schedule

| # | Milestone | Trigger | Amount (₱) | Amount (USD) |
| --- | --- | --- | --- | --- |
| 1 | Project Kickoff | Signed agreement + requirements sign-off | ₱411,840 | $7,289 |
| 2 | Backend Completion (Nexus) | Nexus API + Admin Dashboard functional; Krypton POS integration verified | ₱343,200 | $6,074 |
| 3 | All Apps Complete | Grillpad + Print Bridge built; end-to-end order flow working on LAN | ₱343,200 | $6,074 |
| 4 | UAT Sign-Off | Client acceptance testing passed; system deployed on Pi | ₱205,920 | $3,645 |
| 5 | Go-Live + Documentation | System live in restaurant; full documentation delivered | ₱68,640 | $1,215 |
| DEVELOPMENT TOTAL (100%) |  |  | ₱1,372,800 | $24,297 |

Hardware billed separately Hardware is procured and invoiced separately from development. Client may opt to self-procure hardware using the specification list in Section 4. Developer can assist with procurement at no markup if preferred.

## 8.2  Terms

- Payment terms: 14 days from milestone delivery.

- Rates are fixed for the duration of this engagement (valid 90 days from quotation date).

- Out-of-scope features requested after contract sign-off are billed at the same hourly rate with written approval.

- Source code is transferred to the client upon final payment of the development total.

- 1 month of post-launch defect warranty is included — bugs found within 30 days of go-live are fixed at no charge.

- Hardware warranty is governed by each manufacturer's warranty terms.

# 9. What the Client Receives

The following is a complete list of deliverables included in this engagement at no additional cost.

## 9.1  Software Deliverables

| Deliverable | Description | Format |
| --- | --- | --- |
| Grillpad (Tablet Ordering PWA) | Full Nuxt 3 source code; production-ready PWA build; Docker service config | Source code + Docker |
| Nexus (Admin Dashboard + API) | Full Laravel 12 source; 291 PHP files; 61 controllers; 78 migrations; admin panel | Source code + Docker |
| Print Bridge (Flutter Android) | Full Flutter/Dart source; compiled APK for sideloading on Android device | Source + APK |
| Docker Compose Platform | Full 9-service compose.yaml; Nginx config; deploy scripts; Pi environment setup | Config + scripts |
| 5 Cross-App Contract Files | order-state, tablet-api, printer-relay, pos-db, auth-session — governs all inter-app surfaces | Markdown docs |
| Pre-Merge Validation Gates | scripts/pre-merge-check.sh (Bash) + .ps1 (PowerShell) — automated code validation | Shell scripts |

## 9.2  Documentation Deliverables

| Document | Contents | Format |
| --- | --- | --- |
| BRD v1.0 — Legacy Proposal | Original design proposal (KDS-based) — historical reference | Word .docx |
| BRD v2.0 — Production | Full BRD/URS: requirements, use cases, DB schema, workflows, user manual, Krypton SPs, recommendations | Word .docx |
| Technical Insights Reference | Sequence diagrams, state machines, ERD, topology maps, frameworks, integration patterns | Word .docx |
| Project Cost Estimate | This document — full cost breakdown, hardware, licensing, comparison, payment terms | Word .docx |
| API Documentation | All endpoints, auth methods, request/response schemas, error codes | Markdown |
| User Manual | Non-technical staff guide: admin dashboard, order management, devices, reports, troubleshooting | In BRD v2 |
| Operational Runbook | Pi deployment, Docker management, backup procedures, failure recovery steps | Markdown |

Client Ownership — No Vendor Lock-In All source code is transferred to the client on final payment. All documentation is delivered in open formats (Word, Markdown, PDF). No proprietary platform dependency — the system runs on standard open-source software. Any Laravel/Nuxt/Flutter developer can maintain the system after handover. All data remains on the client's own hardware — Raspberry Pi on their LAN.